**Timeline for Grant Recipients**

|  |  |
| --- | --- |
| **Date / Time** | **Event** |
| Friday 10 January 2025  10am to 1pm | Community Chest for Social Prescribing Information Day  Barking Learning Centre Conference Centre |
| Monday 20 January 2025  5pm | Deadline for grant applications for the Community Chest |
| Thursday 23 January 2025 | Review grant applications by Steering Group |
| Friday 24 January 2025 | Invite confirmation to be sent to successful organisations to attend Participatory Budgeting event |
| Thursday 27 February 2025 | Additional Participatory Budgeting Event – Barking Learning Centre  1pm to 5pm depending on number of applications |
| Friday 28 February 2025 | Participatory Budgeting Event – Barking Learning Centre  10am to 4pm |
| Week Commencing  3 March 2025 | Confirmation of success sent to organisations, funding process and next steps |
| 10 March to 31 July 2025 | Activities delivered and evaluation started |
| August 2025 | Monitoring and evaluation complete  Report written by Steering Group and Council team |
| September 2025 | Appointment of new Steering Group for 2025 – 2026 programme |